## Read Me
AnimalCafe Phase 6 — Studio Owner manual review
Status | acceptance pending
Manual rows | P6-M-001–030 exactly once
Result cells | actual / verdict / evidence / notes intentionally blank
Physical Touch | required for hand feel, gesture ownership and physical Safe Area
Simulation boundary | virtual Touch and RenderTexture captures are supporting evidence only
Canonical Scene | production Assets/Scenes/MainCafe.unity
Unity | 6000.5.5f1
Task 10 state | awaiting independent Art/QA review and Studio Owner acceptance
Workbook limitation | @oai/artifact-tool 2.8.6 export does not persist freeze panes; no frozen pane or ID column is claimed. Table filters and verdict dropdown remain available.

## Manual Review
P6-M-001–030 Manual Review
Acceptance pending — fill actual, one verdict, evidence path and notes only during Studio Owner execution.
ID | Scene / resolution / device | precondition | action | expected | actual | PASS / FAIL / BLOCKED | evidence path | notes
P6-M-001 | MainCafe / Windows / record actual resolution / Mouse | Game Time running at a known speed; Decoration Mode closed. | Click Decor; observe the full right rail, Catalogue entry motion and Grid; then click Done. | Confirm the rail order is Done / indicator / Pause / 1× / 2×; Pause is visibly selected, 1× / 2× are disabled, Catalogue is Expanded, and Done restores the exact pre-entry speed without overlap or clipping.
P6-M-002 | MainCafe / Windows / record actual resolution / Mouse | Decoration Mode open; Catalogue Expanded; no active Preview. | Inspect all four Counter tiles and the current player-visible copy; select one tile and hover each floating action symbol. | Confirm recognizable previews, consistent angle, clear 1 × 1 / 1 × 2 / 1 × 3 / 2 × 3 footprints, readable English copy, and exact English tooltips Store / Cancel / Rotate / Confirm where each action is available; do not infer Chinese-localization acceptance.
P6-M-003 | MainCafe / Windows / record actual resolution / Mouse | Fresh Expanded Catalogue; no active Preview. | Select 1 × 1, left-drag it across multiple cells, use Mouse Wheel once, then click Rotate and Confirm. | Confirm Catalogue collapses to its visible handle; Preview follows Mouse with visible footprint/placement feedback; Wheel affects only Camera zoom; floating actions stay near the Preview without covering the right rail; Confirm creates exactly one formal furniture.
P6-M-004 | MainCafe / Windows / record actual resolution / Mouse | Fresh Expanded Catalogue; no active Preview. | Select 1 × 2, left-drag it, Rotate to 2 × 1, move again and Confirm. | Confirm the two-cell highlight and model move together, rotation updates to 2 × 1, the floating actions remain reachable and non-overlapping, and Confirm produces one unstretched formal instance.
P6-M-005 | MainCafe / Windows / record actual resolution / Mouse | Fresh Expanded Catalogue; no active Preview. | Select 1 × 3, left-drag it, Rotate to 3 × 1, move again and Confirm. | Confirm the three-cell highlight and model move together, rotation updates immediately, the floating actions remain reachable and non-overlapping, and Confirm produces one unstretched formal instance.
P6-M-006 | MainCafe / Portrait / eligible Touch device | Fresh Catalogue state; no active Preview. | Select and place `2 × 3`；Rotate once；move and Confirm。 | Confirm six-cell highlight、rotation to `3 × 2` and readable footprint in Portrait。
P6-M-007 | MainCafe / record actual / eligible Touch device | Initial `1 × 1 Counter Module` formal furniture present; no active Preview. | Tap initial `1 × 1 Counter Module`。 | Confirm immediate suspended Preview and compact action bar。
P6-M-008 | MainCafe / record actual / physical Touch required | Each of the four sizes is available in a fresh Preview state. | Drag every size。 | Confirm finger does not hide furniture / footprint and Preview position feels connected to Touch。
P6-M-009 | MainCafe / record actual / eligible Touch device | Active Preview on a valid cell. | Inspect valid placement feedback。 | Confirm green plus non-color cue is clear without overpowering Floor / furniture art。
P6-M-010 | MainCafe / record actual / eligible Touch device | Active Preview; another formal furniture is available for overlap. | Overlap another furniture。 | Confirm red plus non-color cue、specific `这里已有家具` message and disabled Confirm。
P6-M-011 | MainCafe / record actual / physical Touch required | Each asymmetric size is available in a fresh Preview state. | Drag every asymmetric size across multiple Floor edges。 | Confirm correct cells and `超出可装修区域`。
P6-M-012 | MainCafe / record actual / eligible Touch device | Active multi-cell Preview; Entrance Clearance visible. | Drag a multi-cell preset into the Entrance zone。 | Confirm placement is blocked and reason is specific。
P6-M-013 | MainCafe / record actual / eligible Touch device | Active Preview positioned near an obstacle. | Rotate from valid to invalid and back。 | Confirm center does not jump far、highlight updates immediately and no hidden Confirm occurs。
P6-M-014 | MainCafe / record actual / eligible Touch device | Initial Counter formal furniture present; record its original position / rotation. | Move and rotate initial Counter；Cancel。 | Confirm exact original position / rotation returns。
P6-M-015 | MainCafe / record actual / eligible Touch device | Fresh Catalogue state; no active Preview. | Select a new preset；move；Cancel。 | Confirm it disappears completely and Catalogue returns。
P6-M-016 | MainCafe / record actual / eligible Touch device | Furniture A and B are selectable; no active Preview. | Edit A then tap B。 | Confirm A automatically returns / disappears as applicable and B becomes the only active Preview。
P6-M-017 | MainCafe / record actual / eligible Touch device | Run once with an active Preview and once with no Preview. | With active Preview, tap blank Floor。Without Preview, tap blank Floor。 | With active Preview, confirm nothing is cancelled。Without Preview, confirm ordinary selection clears。
P6-M-018 | MainCafe / record actual / eligible Touch device | Existing formal furniture selected in active Preview. | Tap Store；while Modal is open, tap its blocking backdrop directly over a selectable lower-layer furniture or Floor to dismiss；confirm that release does not pass through；reopen and confirm Store。 | Confirm the blocking backdrop owns the dismiss input：lower Catalogue / Action Bar / Scene receives no selection、movement、Preview restart or action；fresh input remains usable；final Store removes only the selected furniture。
P6-M-019 | MainCafe / record actual / eligible Touch device | Existing furniture moved but not confirmed. | Exit Decoration Mode。 | Confirm original position returns and no warning Modal appears。
P6-M-020 | MainCafe / record actual / eligible Touch device | Decoration Mode open; multiple changes ready to Confirm. | Confirm multiple changes；exit and re-enter Decoration Mode。 | Confirm the current runtime Layout remains。
P6-M-021 | MainCafe / record actual / physical Touch required | Decoration Mode open; no active Preview; blank Floor visible. | Single-finger drag from blank Floor。 | Confirm only Camera moves。
P6-M-022 | MainCafe / record actual / physical Touch required | Decoration Mode open; selectable furniture visible. | Single-finger drag from Furniture。 | Confirm Furniture moves and Camera stays stable except approved edge auto-pan。
P6-M-023 | MainCafe / record actual / physical two-finger Touch required | Active Furniture drag in progress. | Add second finger and Pinch。 | Confirm Camera zooms、Furniture stays pending and no Confirm / Cancel occurs。
P6-M-024 | MainCafe / record actual / physical Touch required | Each furniture size available; each usable viewport edge identified. | Drag each furniture size near all usable viewport edges。 | Confirm direction、activation zone、speed curve and stop behavior feel controllable。
P6-M-025 | MainCafe / physical device Safe Area / physical Touch required | Catalogue and action bar can be opened; active Preview available. | Exercise Catalogue / action bar transitions near device edges。 | Confirm Catalogue / action bar transitions do not hide furniture or essential actions；Safe Area does not cause edge-pan misfires。
P6-M-026 | MainCafe / `1080 × 1920`, `720 × 1280`, `1080 × 2400` / record runner or device | Fresh equivalent state at each Portrait size. | Check reference、small and tall Portrait。 | Confirm no clipping、overlap or unreachable controls。
P6-M-027 | MainCafe / `2400 × 1080` / record runner or device | Fresh Landscape fallback state. | Review the full Decoration action flow in Landscape。 | Confirm all actions remain usable and readable without requiring final Landscape polish。
P6-M-028 | MainCafe / record actual / Studio Owner | Do not read implementation notes before this case. | Select、drag、rotate、confirm、cancel and store；record any confusing label or hidden state。 | Confirm it is clear how to perform every action without implementation notes。
P6-M-029 | MainCafe / record actual / eligible Touch device | Canonical initial Layout; Game Time running. | Enter / exit twice；perform Confirm、Cancel and Store across sessions。 | Confirm no duplicate UI、Grid、Furniture、permanent Pause or broken input。
P6-M-030 | MainCafe / record actual / eligible Touch device | Fresh mixed-placement session; Console open for final review. | Complete a mixed placement session and resume Game Time。 | Console must contain no unexpected Error / Exception or unexplained Warning。

## Tuning Record
Phase 6 Manual Tuning Record
Accepted values / observations begin blank. Rerun affected focused tests and manual cases after any accepted change.
tuning field | accepted value / observation | affected manual cases | evidence path | notes
Preview hover height |  | P6-M-003–016, P6-M-022–024
touch drag offset |  | P6-M-008, P6-M-011, P6-M-022–024
drag threshold |  | P6-M-003–008, P6-M-021–024
edge auto-pan zone |  | P6-M-011, P6-M-024–025
edge auto-pan speed curve / maximum speed |  | P6-M-011, P6-M-024
Bottom Sheet collapsed / action height |  | P6-M-001–002, P6-M-007, P6-M-025–027
Grid line opacity |  | P6-M-001, P6-M-009–012
valid / invalid intensity |  | P6-M-009–013
transition timing |  | P6-M-001, P6-M-015, P6-M-018, P6-M-025, P6-M-028
Portrait Camera framing and furniture readability |  | P6-M-003–008, P6-M-020, P6-M-026